H.J. Baker & Bro., LLC

AP Invoice Processing Platform

Statement of Work

Scope, deliverables, delivery approach, responsibilities, commercials and acceptance for the implementation. Product functionality is defined in the companion PRD.

1 August 2026

Prepared by Alferix

Document control

Document information

| Document | Statement of Work |
| --- | --- |
| Project | AP Invoice Processing Platform |
| Version | 1.1 |
| Date | 1 August 2026 |
| Prepared by | Alferix |
| Client | H.J. Baker & Bro., LLC |
| Companion document | Product Requirements Document v1.1 |
| Status | For client review |

Revision history

| Version | Date | Author | Summary of change |
| --- | --- | --- | --- |
| 1.0 | 31 Jul 2026 | Alferix | First issue |
| 1.1 | 1 Aug 2026 | Alferix | Restructured to a standard delivery-focused SOW; product functionality now referenced from the PRD rather than repeated |

Table of contents

1	Executive summary	4

2	Project objectives	4

3	Scope of work	4

3.1	Included	4

3.2	Excluded	5

4	Deliverables	5

5	Product scope	6

6	Project phases	6

7	Timeline	7

7.1	Key milestones and gates	7

8	Roles and responsibilities	8

8.1	Governance	8

9	Assumptions	9

10	Dependencies	9

11	Acceptance criteria	9

12	Support and warranty	10

13	Change management	10

14	Commercials	10

14.1	Project cost breakdown	11

14.2	Azure infrastructure run cost	11

14.3	Payment milestones	12

14.4	Invoicing schedule	12

15	Sign-off	12

# Executive summary

### Purpose

This Statement of Work (SOW) defines the scope, deliverables, implementation approach, responsibilities, commercial assumptions and acceptance criteria for the implementation of the AP Invoice Processing Platform for H.J. Baker & Bro., LLC.

This SOW should be read together with the Product Requirements Document (PRD v1.1). Where a conflict exists, the PRD defines product functionality and this SOW defines project delivery.

Table 1. Engagement at a glance

| Approach | Phased delivery in short increments, with a working system shown at the end of each |
| --- | --- |
| Indicative duration | 13 weeks from kickoff to go-live, then hypercare |
| Supplier | Alferix, design, build, integration, testing, deployment and support |
| Client | H.J. Baker & Bro., LLC |
| Governs functionality | Product Requirements Document v1.1 |

# Project objectives

The engagement exists to deliver the following business outcomes. The measures and targets behind them are defined in the PRD (Section 2) and are not restated here.

- Replace Blue Creek (Vision360) as the AP processing tool.

- Reduce manual AP effort, in particular the line-by-line coding done in Sage today.

- Increase straight-through processing of routine invoices.

- Integrate directly with Sage X3 for master data, document creation and payment feedback.

- Improve operational visibility and auditability across all AP activity.

- Standardise AP processing across the seven operating companies.

# Scope of work

Scope is expressed here as delivery activities. The functional behaviour each activity implements is specified in the PRD (see Section 5).

## Included

- Solution design and technical architecture.

- User-interface development for the queues, document detail, search and administration screens.

- Backend development of the processing engine and the five document flows.

- AI extraction and OCR integration for header and line capture with per-field confidence.

- AI classification and rule-based routing.

- Sage X3 integration, master-data reads, document creation with attachment, and payment feedback.

- Approval workflow, including hierarchy, limits, delegation and AP final review.

- Dashboards and reporting.

- User and role management.

- Testing, system integration testing and support for user acceptance testing.

- Deployment to the client's environments.

- Hypercare following go-live.

## Excluded

- Customisation or development inside Sage X3 (carried out by Net at Work).

- Cloud infrastructure is a commercial option, not a fixed exclusion: it is provided by Alferix under Option 1 and by H.J. Baker under Option 2 (Section 14).

- Vendor onboarding and supplier master maintenance.

- Data cleansing of existing master or transactional data.

- Historical data migration from Blue Creek beyond open in-flight items.

- User training beyond the agreed enablement sessions.

- Purchase-order creation, which is confirmed as manual (PRD Section 9).

# Deliverables

Each phase produces a defined, acceptable deliverable.

Table 2. Deliverables by phase

| Phase | Deliverable | Description |
| --- | --- | --- |
| Discovery and design | Solution design and architecture | Validated requirements, confirmed Sage integration contract, PRD baseline, approved screen designs and API design |
| Development | AP platform | The working platform: engine, five flows, AI extraction and classification, UI |
| Integration | Sage X3 interfaces | Live master-data reads, document creation with attachment, write-back and payment feedback |
| Testing | UAT build | A tested build with system-integration testing complete and UAT supported |
| Deployment | Production release | The platform deployed and live for the first company, then rolled out |
| Closure | Documentation and handover | Administrator and user documentation, runbooks and knowledge transfer |

# Product scope

The product functionality delivered under this engagement is specified in the Product Requirements Document version 1.1 and is not restated in this SOW. The functional areas in scope, and where each is defined, are listed below.

Table 3. Functional scope and where it is defined

| Functional area | Defined in the PRD |
| --- | --- |
| PO invoice processing | Section 8 |
| Non-PO processing | Section 9 |
| Prepayments | Section 10 |
| Credits | Section 11 |
| Rebills | Section 12 |
| Intake, extraction and classification | Sections 6-7 |
| Search and audit | Section 13 |
| Reporting | Section 14 |
| Administration, routing rules, templates, reference lists, users | Sections 6, 7, 13 |

Precedence. Where this SOW and the PRD differ, the PRD governs product functionality and this SOW governs delivery. Anything not documented in the PRD, or in an approved change request, is out of scope (Section 13).

# Project phases

Five phases, delivered in short increments with a working system demonstrated at the end of each.

Table 4. Phases and their deliverables

| Phase | Focus | Key deliverables |
| --- | --- | --- |
| 1. Discovery and design | Confirm requirements and the Sage contract, and design the solution | Workshops; requirement validation; PRD baseline; UX, architecture and API design |
| 2. Development | Build the platform | Core platform; AI engine; Sage integration |
| 3. Testing | Prove it works | System integration testing; user acceptance testing; defect resolution |
| 4. Go-live | Deploy and stabilise | Production deployment; hypercare |

# Timeline

Indicative durations from an agreed kickoff. Phases overlap where dependencies allow; dates firm up at the end of Discovery.

Table 5. Indicative timeline

| Phase | Duration |
| --- | --- |
| Discovery and design | 2 weeks |
| Development | 8 weeks |
| Testing | 2 weeks |
| Go-live | 1 week |
| Total to go-live | 13 weeks |

Hypercare runs for a further four weeks after go-live (Section 12). Company-by-company rollout is sequenced with the client to avoid quarterly true-up windows.

## Key milestones and gates

Each milestone is a gate: the engagement does not proceed past it until its condition is met and accepted.

Table 6. Delivery milestones

| Milestone | When | Gate, accepted when |
| --- | --- | --- |
| Design sign-off | End of Discovery and design | Solution design, architecture and the PRD baseline are approved, and the Sage integration contract is confirmed |
| Integration proven | During Development | A purchase invoice and a credit memo are created in the Sage test instance with attachment and number returned |
| Development complete | End of Development | All five document flows are demonstrated end to end and system-integration testing has passed |
| UAT sign-off | End of Testing | The client test pack passes with no open critical or high-severity defects |
| First company live | Go-live | One company is processing production documents into Sage |
| Hypercare complete | Go-live + 4 weeks | Four weeks in production; the objective measures (PRD Section 2) are reported |

# Roles and responsibilities

Both parties commit named people for the duration of the engagement.

Table 7. Responsibilities

| H.J. Baker & Bro., LLC | Alferix |
| --- | --- |
| Business decisions and timely sign-off | Solution design and architecture |
| User acceptance testing by named SMEs | UI and backend development |
| Master data and configuration (hierarchy, limits, templates, mappings) | AI extraction, classification and Sage integration |
| Sage X3 access and Sage-side support (with Net at Work) | Testing, deployment and hypercare |
| Network connectivity to Sage X3; Azure subscription and infrastructure under Option 2 | Hosting and infrastructure under Option 1; project management, documentation and support |

## Governance

The engagement is run through a light, regular governance rhythm so decisions are made when they are needed and progress is visible throughout.

- Weekly working session, the Alferix engagement lead with the H.J. Baker AP team: progress, decisions needed, and a look at what was built.

- Fortnightly increment review, a working demonstration; each increment is accepted or its gaps are listed.

- Monthly steering, with the project sponsor, covering scope, budget, timeline and risk.

- Shared decision log, every open decision carries an owner and a due date; a decision not made by its date becomes a tracked risk.

- Net at Work coordination, a standing item, because the Sage integration is the largest external dependency.

# Assumptions

If an assumption proves untrue, its impact is handled through change control (Section 13).

- Sage X3 exposes the required APIs for master-data reads and document creation, and Net at Work is available to confirm the contract.

- The environments the platform runs in are available: provided by Alferix under Option 1, or in the client's Azure subscription under Option 2.

- Client subject-matter experts are available for workshops, validation and UAT.

- Decisions and approvals are provided within the agreed service level.

- Configuration data is supplied by the client as data, not derived from documents.

- Document volumes and profile are as stated in the PRD (Section 5).

- Extraction uses Claude via the Batch API, as costed in Section 14.

# Dependencies

Delivery depends on the following parties and services being available when needed.

Table 8. Dependencies

| Dependency | Needed for |
| --- | --- |
| Sage team (client) | Access, test data and Sage-side coordination |
| Net at Work | Confirming the Sage X3 API contract and Sage configuration |
| Microsoft 365 | AP mailbox access and single sign-on |
| Microsoft Azure (server and Azure SQL Database) | The runtime the platform is deployed into; provided by Alferix under Option 1, by H.J. Baker under Option 2 |
| AI extraction service (Claude, Batch API) | Extraction of header and line data |

# Acceptance criteria

The project is accepted when the following are met. Feature-level acceptance is defined per document type in the PRD (Sections 8-12).

- User acceptance testing is completed against the agreed test pack.

- All critical and high-severity defects are closed; lower-severity defects are logged with an agreed plan.

- Production deployment is completed and the first company is processing live documents into Sage.

- All contracted deliverables (Section 4) are submitted and accepted.

H.J. Baker has five working days from delivery of each milestone to accept it or to state specific deficiencies in writing; absent either, the milestone is deemed accepted.

# Support and warranty

Alferix provides 30 days of hypercare from go-live, covering defect resolution and close support for the AP team. Defects against this SOW and the PRD reported within the warranty period are corrected at no charge.

Table 9. Severity matrix and response

| Severity | Definition | Response | Resolution target |
| --- | --- | --- | --- |
| 1. Critical | Processing stopped; no workaround | 2 business hours | 1 business day |
| 2. High | Major function impaired; workaround exists | 4 business hours | 3 business days |
| 3. Medium | Minor function impaired | 1 business day | Next release |
| 4. Low | Cosmetic or advisory | 2 business days | Scheduled |

# Change management

Any requirement not documented in the PRD, or not covered by an approved change request, is treated as out of scope and managed through the change-request process.

No change is implemented until it is approved in writing by both the H.J. Baker business owner and the Alferix engagement lead. Minor changes under an agreed threshold are absorbed within the increment at no charge, so small course corrections do not each become paperwork.

Table 10. What a change request records

| Field | Description |
| --- | --- |
| Change | What is changing, and the business reason for it |
| Effort | Impact in person-days |
| Schedule | Impact on the timeline and any dependent milestones |
| Cost | Impact on the fee, at the agreed day rates |
| Approval | Written approval by both parties before any work starts |

# Commercials

Two commercial options are offered. They differ only in who hosts the platform and therefore who bears the cloud infrastructure cost. Both include the full implementation and Alferix's ongoing management and support of the application.

Table 11. Commercial options

|  | Option 1: Hosted and managed by Alferix | Option 2: Hosted by H.J. Baker, managed by Alferix |
| --- | --- | --- |
| Where it runs | Alferix-managed Azure environment | H.J. Baker's own Azure subscription |
| Cloud infrastructure (Azure server and Azure SQL Database) | Provided and paid by Alferix, included in the monthly fee | Provided and paid by H.J. Baker, billed directly by Azure |
| Application management and support | Included | Included |
| Implementation (one-time) | USD 15,000, fixed | USD 46,000 |
| Recurring | USD 5,000 per month | USD 12,000 per year |

## Project cost breakdown

The implementation is delivered in four phases. The effort and cost break down as below. This $46,000 is the implementation fee under Option 2; under Option 1 the up-front is reduced to $15,000, with the balance recovered through the monthly fee.

Table 12. Implementation cost breakdown by phase (USD)

| Phase | Weeks | Days | Cost | Share |
| --- | --- | --- | --- | --- |
| Discovery and design | 2 | 14 | $5,600 | 12% |
| Development | 8 | 78 | $31,200 | 68% |
| Testing | 2 | 16 | $6,400 | 14% |
| Go-live | 1 | 7 | $2,800 | 6% |
| Total | 13 | 115 | $46,000 | 100% |

## Azure infrastructure run cost

The estimated monthly Azure run cost at the target volume of 3,000 documents (about 30,000 pages) a month is set out below. Under Option 1 this cost sits inside Alferix's monthly fee; under Option 2 it is billed directly to H.J. Baker by Azure.

Table 13. Monthly run cost at 3,000 documents / 30,000 pages (USD)

| Component | Configuration | Low | High |
| --- | --- | --- | --- |
| Frontend | Static Web Apps, Standard | $9 | $9 |
| Backend | App Service P1v3 Linux (low = 1-year reserved) | $74 | $113 |
| Database | Azure SQL, General Purpose serverless 1-4 vCore, auto-pause | $200 | $260 |
| File storage | Blob, ~120 GB year one, lifecycle to cool then archive | $8 | $15 |
| Platform services | Key Vault, App Insights, backups, egress | $35 | $45 |
| AI extraction | Claude, Batch API with prompt caching | $425 | $508 |
| Total per month |  | $751 | $950 |

Assumptions behind these figures:

- 3,000 documents × 10 pages = 30,000 pages, about 3,000 tokens per page all-in (text plus page image), and about 3,000 output tokens per document.

- Batch API throughout (50% discount), valid because the pipeline is asynchronous and matches the hourly Sage cycle.

- Sonnet 5 priced at the standard $3 / $15 rate effective 1 September 2026; until then this line runs about $110 lower.

- Single region, with no zone redundancy, geo-replica or private endpoints; adding high availability takes the total past $1,500.

- $0.15 to $0.19 per document all-in, of which AI is roughly $0.09 to $0.10.

## Payment milestones

The one-time implementation fee is invoiced against two milestones, whichever option is chosen. Recurring fees begin at go-live.

Table 14. Implementation fee payment schedule

| Milestone | Share of implementation fee |
| --- | --- |
| Contract signature | 50% |
| Production go-live | 50% |
| Total | 100% |

## Invoicing schedule

- Under Option 1, the recurring fee is invoiced monthly in advance, beginning at go-live.

- Under Option 2, the support fee is invoiced annually in advance, beginning at go-live.

- Payment terms are 30 days from the date of invoice.

- All figures are in US dollars and exclusive of applicable sales, use, VAT and GST taxes.

# Sign-off

By signing below, the parties agree to the scope, deliverables, timeline and commercials set out in this Statement of Work, read together with the Product Requirements Document v1.1.

Signed for and on behalf of the parties below.

| H.J. BAKER & BRO., LLC Project Sponsor Name and title Signature Date Project Manager Name and title Signature Date | ALFERIX Project Manager Name and title Signature Date Delivery Head Name and title Signature Date |
| --- | --- |